## 5 YEAR DEF. MAINT PLAN
CENTENARY COLLEGE DEFERRED MAINTENANCE AND CAPITAL NEEDS
2019-2023 5-YEAR PLAN
Total All Cost:
|  |  | Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5 | 5 Year Total | Years 6+ | Total All
CENTENARY COLLEGE DEFERRED MAINTENANCE
FY2020-2024 5-YEAR PLAN
|  |  | fy2019-2020 | fy2020-2021 | fy2021-2022 | fy2022-2023 | fy2023-2024 | 5-year Total | Years 6+ | Total
|  | Academic and Support Buildings | 403500 | 230000 | 315000 | 385000 | 425000 | 1673500 | 7270000 | 9250500
|  | Athletic Buildings | 50900 | 30000 | 10000 | 40000 | 60000 | 190900 | 2725000 | 2915900
|  | Resident Halls | 104000 | 273000 | 200000 | 125000 | 25000 | 717000 | 7685000 | 8402000
|  |  | 558400 | 533000 | 525000 | 550000 | 510000 | 2581400 | 17680000 | 20568400
Note: The list below identifies known deferred maintenance for each building. Many of the projects are directly related to deferred maintenance while others also include building enhancements. Fire Code, ADA, system failures and energy conservation are major factors in our projects. Priorities can adjust year to year based on most critical needs and available funding.
|  |  | Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5 | 5-YEAR |  | TOTAL DEF.
Deferred Maintenance List: |  |  | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | TOTAL | YEARS 6+ | MAINT | DISCRIPTION/JUSTIFICATION
ACADEMIC AND SUPPORT FACILITIES
Anderson Choral
|  | Paint Halls |  | 15000 |  |  |  | 15000 |  | 15000 | Needs updating
|  | Install Energy Controls |  |  |  |  | 25000 | 25000 |  | 25000 | Work to complete energy controls project.
|  | Convert lighting to LED | [5 empty] | 0 | 80000 | 80000 | High bay lights need change out with LED
Brown Chapel
|  | Roof Replacement |  |  | 40000 |  |  | 40000 |  | 40000 | Roof is older and some shingles are beginning to become bare
|  | Electricial Panel Updates |  |  |  | 10000 |  |  |  |  | This is to update old lectrical panel
|  | Air Handler #2 Replacement |  |  |  |  | 50000 |  |  | 0 | Small air handler needs replaced, and controls added.
|  | Replace Windows in Sanctuary | [5 empty] | 0 | 75000 | 75000 | Windows are not energy efficiant ad have discolored.
|  | Replace Carpet | [5 empty] | 0 | 25000 | 25000 | Carpet startg to show its age.
|  | Renovate Meeting Rooms in Back of Church | [5 empty] | 0 | 10000 | 10000 | Paint, flooring and HVAC.
Bynum Commons
|  | Paint Kitchen Floor | 8000 |  |  |  |  | 8000 |  | 8000 | Floor looks in bad condition for cooking area.
|  | RTU - Condenser repair/replace |  |  | 10000 |  |  | 10000 |  | 10000 | Unit is old and noncompliant with Freon regulations.
|  | Replace Student Area Dining Carpet |  |  |  |  | 40000 | 40000 |  | 40000 | Carpet is aging, stained.
|  | Entry Cover (Capital Request) | [5 empty] | 0 | 75000 | 75000 | Create overhang/awning to cut energy cost & dry space outside doors.
Centenary Square
|  | Re-Roof | [5 empty] | 0 | 100000 | 100000 | Roof in extremely bad shape. Many leaks and repairs.
|  | HVAC Controls Replacement | [5 empty] | 0 | 30000 | 30000 | HVAC controls barely function, out of date.
|  | All Restrooms Need Updating/ADA | [5 empty] | 0 | 100000 | 100000 | Out of date. Need ADA compliance.
|  | New Boiler | [5 empty] | 0 | 100000 | 100000 | Boiler old and in bad shape.
|  | HVAC piping for Heating and Cooling Needs | [5 empty] | 0 | 150000 | 150000 | HVAC piping is old and leaks.
|  | Replace Ceilings in Halls | [5 empty] | 0 | 5000 | 5000 | Old tile.
|  | New Flooring in Hall/Offices | [5 empty] | 0 | 80000 | 80000 | Update interior.
**Complete Renovation or Replacement Needed
Facilities Services
|  | Replace Shop Equipment/Dust Removal | 10000 |  |  |  |  | 10000 |  | 10000 | Equipment is old and lacks safety features, Dust Removal.
|  | Tractor (Fall)and Gator Purchases | 35000 |  |  |  |  | 35000 |  | 35000 | Tractor for landscaping needs and Gator for ath. fields.
Feazel Building
|  | Re-roof and add Drains | 20000 |  |  |  |  | 20000 |  | 20000 | Roof has a number of leaks.
|  | Convert lighting to LED | [6 empty] | 18000 |  | Replacement needed for energy savings.
[8 empty] | 0 |  | 0
Hamilton Hall
|  | Install New Thermostats - | 6000 |  |  |  |  | 6000 |  | 6000 | This Completes Thermostat Replacement in Building,
|  | Clean basement drainage system/add pumps | 10000 |  |  |  |  | 10000 |  | 10000 | To stop flooding.
|  | Repair Roof in several areas | 10000 |  |  |  |  | 10000 |  | 10000 | Repair areas until funding is available for new roof.
|  | Replace Recirculating pump; | 13000 |  |  |  |  | 13000 |  | 13000 | Old and currently leaks.
|  | Address Code Issue w/Rails on Stairs |  | 10000 |  |  |  | 10000 |  | 10000 | Fire Code Issue with Stair Railing (Fire Marshal).
|  | Reroof Building | [5 empty] | 0 | 300000 | 300000 | Roof has aged, underlayment biggest issue- leaks
Hurley Hall
|  | Replace Fan Coil Units (4 per year) |  |  | 20000 | 20000 | 20000 | 60000 |  | 60000 | This would replace critical Fan Coil Unit problems over time.
|  | Add hot water piping to building | [5 empty] | 0 |  | 75000 | Piping for a 4-pipe HVAC system.
|  | Reroof with Shingles and Repair Dormers | [5 empty] | 0 | 125000 | 125000 | Roof has exceeded life expectancy, it is worn and dormers need repairs.
|  | Paint Stairs | [5 empty] | 0 | 10000 | 10000
|  | Replace Bldg. and Auditorium Lights with LED | [5 empty] | 0 | 40000 | 40000 | Converts all lighting to LED
|  | Replace Stairs to Front Door From Woodlawn | [5 empty] | 0 | 50000 | 50000 | Stairs are in bad shape and sinking. Not to code
|  | Install Temperature/Humidity Sensors | [5 empty] | 0 | 5000 | 5000 | To allow us to read temperatures & humidity.
|  | Building Needs ADA Access, Ramp and Drive | [5 empty] | 0 | 200000 | 200000 | Improved access to meet code.
|  | Install an Elevator | [5 empty] | 0 | 200000 | 200000 | Cost will depend on necessary building modifications.
|  | Complete Renovation of 3rd Floor | [6 empty] | 500000 | 500000 | 3rd Floor in need of renovation for program use.
**3rd Floor -Complete Renovation Needed
Jackson Hall
|  | Reroof Building (Corporate est. ) |  | 50000 |  |  |  | 50000 |  | 50000 | Roof is aged, shingles have been blowing off for a few years.
|  | HVAC Study for Air Quality | 14000 |  |  |  |  | 14000 |  | 14000 | Address HVAC and mold issues.
|  | Replace sink faucets and carpet 108 | 5500 |  |  |  |  | 5500 |  | 5500 | Old Fixtures and leaks.
|  | New boiler |  |  |  | 75000 |  | 75000 |  | 75000 | Boiler is aging/ scheduled replacement.
|  | AC System Update/Replacement | [5 empty] | 0 | 300000 | 300000 | Humidity is becoming a problem - causing mold.
|  | New Carpet and Paint for Halls & Faculty Offices | [5 empty] | 0 | 100000 | 100000 | Carpet aging, scheduled replacement.
Marjorie Lyons Playhouse
|  | ADA Womens restroom ADA update | 10000 |  |  |  |  | 10000 |  | 10000 | Complaints from event attendees - no ADA access.
|  | Electricial Panel Updates, demo old | 8000 |  |  |  |  | 8000 |  | 8000 | Address potential fire issues.
|  | Replace Air Handler (3 total) |  |  | 50000 |  |  | 50000 |  | 50000 | Old, rusted and not able to set up controls.
|  | Fire/Smoke Ventilation for Stage | [5 empty] | 0 | 200000 | 200000 | Fire Marshal citations (5) for these items. Need engineer design.
|  | **Build-in 2nd Floor for Costumes | [6 empty] | 500000 | 750000 | Storage needed, currently using rent house.
Magale Library
|  | Replace Tile on Front Porch | 10000 |  |  |  |  | 10000 |  | 10000 | Tile coming up and broken.
|  | Waterproofing North & South Walls | 10000 |  |  |  | 75000 | 85000 |  | 85000 | Water intrusion from rains is damaging carpets.
|  | Ujpdate Lighting, Wiring and Fire Sprinsker Sys. |  |  |  |  | 40000 | 40000 |  | 40000 | Lighting is poor and sprinklers are needed for safety.
|  | 2nd Floor Restrooms Need Updating/ADA |  |  |  |  | 15000 | 15000 |  | 15000 | Fixtures & equipment outdated.
|  | New Chiller in Library Mechanical Room | [5 empty] | 0 | 150000 | 150000 | This allows for a redundant system.
|  | Replace Windows | [5 empty] | 0 | 200000 | 200000 | Building needs energy efficient windows.
Meadows Museum
|  | Replace Air Handler |  |  | 50000 |  |  | 50000 |  | 50000 | Air Handler old, problems.
|  | Reroof Building |  |  |  | 40000 |  | 40000 | 30000 | 70000 | Roof is aging
Mickle Hall
|  | Mech Room Wiring and Replace old Elect Panels | 10000 |  |  |  |  | 10000 | 30000 | 40000 | Updae old panels and address potential fire issues.
|  | Install FCU in Halls (8 total, 2 per floor) | [5 empty] | 0 | 75000 | 75000 | Halls are hot due to lack of AC, units would greatly improve comfort.
|  | Halls - Paint Walls and Replace Carpet 2nd & 3rd fl. | [5 empty] | 0 | 75000 | 75000 | Upgrade wall treatment, replace carpet.
|  | Replace 2 AHU for Basement | [5 empty] | 0 | 150000 | 150000 | Humidity is becoming a problem, units are original to bldg. 1960
Physical Plant (Chiller Plant)
|  | Chiller Controls | 12000 | [7 empty] | No cxontrals available.
|  | Repair Compressor | 13000 | [7 empty] | Compressor leaks.
|  | Re-Roof | [5 empty] | 0 | 25000 | 25000 | Aged.
|  | Add Chiller for Redundancy and Dorms | [5 empty] | 0 | 150000 | 150000 | One Chiller leaves possible outage, adds support for dorms.
[8 empty] | 0 |  | 0
Sam Peters
|  | Re-roof |  |  |  | 25000 |  | 25000 |  | 25000 | Roof has aged.
Smith Hall
|  | Replace (2) old AHUs in attic | [5 empty] | 0 | 150000 | 150000 | Units are old and 2 pipe systems, need 4 pipe systems.
|  | Replace Hall Carpet and Rm. 118 | [5 empty] | 0 | 30000 | 30000 | Upgrade lighting for energy efficiency & replace carpet.
|  | Texture and Paint Walls in Halls | [5 empty] | 0 | 40000 | 40000 | Update halls with repainting.
|  | Re-roof | [5 empty] | 0 | 40000 | 40000
Student Union
|  | Install Energy Controls |  |  | 15000 |  |  | 15000 | 25000 | 40000 | Add new energy controls to SUB.
|  | New Boiler | [5 empty] | 0 | 70000 | 70000 | Priority for boiler replacement. Exceeded life expectancy
|  | New Chiller - 90 Ton | [5 empty] | 0 | 75000 | 75000 | Scheduled replacement, aging
|  | Postal Box Replacements | [5 empty] | 0 | 22000 | 22000 | Quoted price from "Salbury".
Turner Arts
|  | Air Filteration System (Pottery Barn) |  |  |  |  | 5000 | 5000 |  | 5000 | For improved air quality
|  | Replace Flooring in Hallways and 2 classrooms | [5 empty] | 0 | 30000 | 30000 | Flooring in bad shape, floors shift, needs carpeting.
|  | Replace Classroom Carpet/Paint | [5 empty] | 0 | 50000 | 50000 | Flooring in bad shape, floors shift, needs carpeting.
|  | Concrete Floor in Basement Shop | [5 empty] | 0 | 25000 | 25000 | Work area is dirt and needs Concrete flooring, Or clean out.
**Complete Renovaton or Replacement Needed
Wright Building
|  | Structural repairs/leaks | [5 empty] | 0 | 50000 | 50000 | Building is shifting, doors won't open, walls cracked.
|  | Gutters and roof | [5 empty] | 0 | 25000 | 25000 | Repair gutters/roof.
|  | Replace flooring and Window blinds | [5 empty] | 0 | 75000 | 75000 | Building needs new flooring, HVAC, painting & roofing.
|  | Repair and Paint walls | [5 empty] | 0 | 40000 | 40000 | Walls are in Need of Repairs. New paint.
|  | Retaining wall replacement | [5 empty] | 0 | 10000 | 10000 | Retaining wall is falling in.
**Complete Renovation or Replacement Needed
| 2910 | Currently Closed
**Complete Renovation or Replacement Needed
Campus Wide
|  | ANNUAL: Replace Underground Electricial & Transformers | 60000 | 50000 | 50000 | 50000 | 50000 | 260000 | 350000 | 610000 | Replace old underground high voltage, causing power failures
|  | ANNUAL: Replace Classroom Chairs | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 |  | 75000 | Continuing process for campus updates
|  | ANNUAL:ADA Updates-(Brown Chapel-Sidewalk) | 25000 | 25000 | 25000 | 25000 | 25000 | 125000 |  | 125000 | Continuing process for campus updates
|  | ANNUAL: Asbestos Removal | 25000 | 25000 | 25000 | 25000 | 25000 | 125000 |  | 125000 | Continuing process for campus updates
|  | ANNUAL: Install LED lighting/Outdoor Lighting | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 | 25000 | 100000 | 500-4ft bulbs, Bollards, Dome lights, Fit. Lights, Motion sensor switches, Emer Lights, GFI plugs,
|  | ANNUAL: LABOR to support summer projects | 5000 |  |  |  |  | 5000 |  | 5000 | To support summer projects with short completion time
|  | Replace Athletic Storage Bldg. | 35000 |  |  |  |  | 35000 |  | 35000 | Building not secure and is rotting.
|  | Elevator Repairs-Phones, pit ladders & Pumps, etc | 10000 |  |  |  |  | 10000 |  | 10000 | Mickle, Rotary and Fitness Center
|  | Mechanical Room Circulating Pumps/VFD | 9000 | 10000 |  |  |  | 19000 |  | 19000 | Phase protection | 57000
|  | Bollard Lights Need Replaced |  | 10000 |  | 10000 |  | 20000 |  | 20000 | Replaces old furniture
|  | Mechanical Room leaking valves |  | 20000 |  |  |  | 20000 |  | 20000 | Convert to LED for energy savings.
|  | Electricial Termographic Hot Testing (every 3yrs) |  |  |  | 25000 |  | 25000 |  | 25000 | Routine process
|  | Correct drainage around buildings |  |  |  | 50000 |  | 50000 | 50000 | 100000 | Below Grade flooding issues
|  | Sidewalk widening & repairs |  |  |  |  | 25000 | 25000 | 100000 | 125000 | Level landings at building entries to meet Fire Marshal codes.
|  | Replace Vault Transformers at Hardin (Switch), James, MLP, Library, Mickle and Cline | [5 empty] | 0 | 1000000 | 1000000 | Transformers are 50+ years old and need to be moved outside.
|  | Air Handlers | [5 empty] | 0 | 500000 | 500000 | Add signage in buildings to meet ADA code.
|  | Update Signage in Buildings | [5 empty] | 0 | 60000 | 60000 | Exterior handrails to meet ADA/Life Safety codes.
|  | Handrails | [5 empty] | 0 | 100000 | 100000 | Relocate 2 power poles near Hardin to avoid damage to Oak trees.
|  | Cent. Blvd. - relocate power poles | [5 empty] | 0 | 25000 | 25000 | Campus wide electrical inspection for hot electrical panels.
|  | Update Energy Program Software & Storage | [5 empty] | 0 | 40000 | 40000 | Continuing process for campus updates
|  | Total All Projects | 403500 | 230000 | 315000 | 385000 | 425000 | 1673500 | 7270000 | 9250500
ATHLETICS:
Fitness Center
|  | Chiller Repairs and New Fans | 7900 |  |  |  |  | 7900 |  | 7900 | Repairs and fans are out.
|  | Hot Tub Circulation Pump Replacement/chem. | 11000 |  |  |  |  | 11000 |  | 11000 | Hot Tub has not worked in years, repairs will allow it to heat.
|  | Re-Roof Pool/Porch | 7000 |  |  |  |  | 7000 | 75000 | 82000 | Roofing material is breaking down and aged
|  | Access Ramp Support Post and paint. |  | 25000 |  |  |  | 25000 |  | 25000 | Supporting structure is beginning to rust and flake
|  | Gym Floor Cover Replacement |  |  |  | 30000 |  | 30000 |  | 30000 | Carpeting is worn, stained and has frayed edges.
|  | Replace Running Track Surface |  |  |  |  | 60000 | 60000 |  | 60000 | Covering has aged, stained and looks old.
|  | Add Boiler for Pool | [5 empty] | 0 | 70000 | 70000 | Evaluate the need boiler to heat pool.
|  | Replace Tile Flooring, Carpet and paint | [5 empty] | 0 | 75000 | 75000 | Areas due for an update, flooring aging.
Gold Dome
|  | Paint Gym, halls and Stairs | [5 empty] | 0 | 60000 | 60000 | Wall are dated. Needs fresh coat of paint.
|  | Re-tile halls and Re-carpet Offices & Classroom | [5 empty] | 0 | 100000 | 100000 | Flooring is dated and damaged in some areas.
|  | Update and Renovate Locker-Rooms | [5 empty] | 0 | 100000 | 100000 | All team locker-rooms need updating
|  | Overhaul or Replace Chiller #1 | [5 empty] | 0 | 120000 | 120000 | Chiller age is becoming a concern. This replace 1 of 2.
|  | Overhaul or Replace Chiller #2 | [5 empty] | 0 | 120000 | 120000 | Replace chiller #2.
|  | Dome needs new LED lighting. | [5 empty] | 0 | 80000 | 80000 | Need LED lighting to cut energy cost.
|  | Ramp to back door. | [5 empty] | 0 | 10000 | 10000
|  | Recoat Dome Roof | [5 empty] | 0 | 80000 | 80000 | Roof needs to be evaluated
|  | Replace old fixtures in 2 Restrooms | [5 empty] | 0 | 10000 | 10000 | Fixtures are old.
|  | Ceiling Repairs/Replacement | [5 empty] | 0 | 50000 | 50000 | Dome ceiling is in bad shape, need work.
|  | Replace Upper Level of Chairs | [5 empty] | 0 | 40000 | 40000 | Chairs are old and dated.
|  | Overhaul or Replace Boiler | [5 empty] | 0 | 75000 | 75000 | Boiler is aging, has issues to maintain temp.
|  | Parking lot Repairs/Overlay | [5 empty] | 0 | 500000 | 500000 | Parking in bad shape and limited.
|  | Overlay Shehee Parking lot | [5 empty] | 0 | 50000 | 50000
|  | Overlay Tennis Court Parking lot | [5 empty] | 0 | 50000 | 50000
| Capital | Expand Parking in Grass lot with Concrete | [5 empty] | 0 | 1000000 | 1000000 | Add parking to address shortage
| Capital | Landscape development for Dome | [5 empty] | 0 | 40000 | 40000 | Dome needs landscaping, irrigation and lighting.
[8 empty] | 0 |  | 0
McCarthy Baseball
[8 empty] | 0 |  | 0
|  | Install new Code Compliant Exterior Stairs |  |  | 10000 |  |  | 10000 |  | 10000 | Egress is a code issue for the building.
**Complete Renovation or Replacement Needed
[8 empty] | 0 |  | 0
Baseball Complex | [7 empty] | 0 |  | 0
|  | Repairs to pressbox |  | 5000 |  |  |  | 5000 |  | 5000 | Exterior is rotting.
|  | Concession/Bathrooms Repairs | 5000 |  |  | 10000 |  | 15000 |  | 15000
[8 empty] | 0 |  | 0
Jones Rice Practice | [7 empty] | 0 |  | 0
|  | Water Well Needed | 20000 |  |  |  |  | 20000 |  | 20000 | Water bill is high. Well to cut cost and sewage expense.
[8 empty] | 0 |  | 0
Soccer/Lacrosse | [7 empty] | 0 |  | 0
|  | Under Renovation | [5 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
Softball Complex | [7 empty] | 0 |  | 0
|  | Under Renovation | [8 empty] | Fence in bad shape.
[8 empty] | 0 |  | 0
Tennis Complex | [7 empty] | 0 |  | 0
|  | Need Practice Wall N/E Corner | [5 empty] | 0 | 20000 | 20000 | Need for practice wall and elimindate winds from damaging screens.
|  | Total | 50900 | 30000 | 10000 | 40000 | 60000 | 190900 | 2725000 | 2915900
RESIDENT HALLS:
CLINE HALL
|  | Replace mattresses | 4000 |  |  |  |  | 4000 |  | 4000
|  | Fire Sprinkler System in Attic |  |  | 75000 |  |  | 75000 |  | 75000
|  | Mech Room Electic Panel Repalcements |  |  | 25000 |  |  | 25000 |  | 25000
|  | Replace Steps and Sidewalks |  |  | 25000 |  |  | 25000 |  | 25000 | Cracked, uneven and slanted stairs are unsafe
|  | Replace Fan Coil Units | 20000 | 20000 |  |  |  | 40000 | 100000 | 140000
|  | Replace plumbing to Suites | [5 empty] | 0 | 200000 | 200000
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Replace Parking Lot W/Concrete | [5 empty] | 0 | 175000 | 175000 | Asphalt in bad shape, has lots of repairs. Visible.
|  | Hall Director HVAC Unit | [5 empty] | 0 | 10000 | 10000 | Apartment HVAC for when building is vacant.
|  | Replace 2nd & 3rd Fl. Room doors | [5 empty] | 0 | 15000 | 15000 | Most door are in bad shape, completes to match 1st.
|  | Shower Partitions Need Repairs | [5 empty] | 0 | 15000 | 15000 | Need to repalce many of them.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Renovate Basement for Staff | [5 empty] | 0 | 60000 | 60000 | Allow for more available beds.
HARDIN HALL
|  | Replace Carpet on Porch |  | 8000 |  |  |  | 8000 |  | 8000 | Carpet is old and stained.
|  | Mech Room Electric Panel Replacement |  |  | 25000 |  |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  |  |  |  | 25000 | 25000 |  | 25000 | Some shower inserts need replaced. Mold/busted pans are biggest issue
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 75000 | 75000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Hall Carpet Replacement | [5 empty] | 0 | 25000 | 25000 | Hall carpet is old and in need of replacement.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
JAMES ANNEX
|  | Replace Chiller | 75000 |  |  |  |  | 75000 |  | 75000 | Chiller is old and failing. Fails with heavy loads.
|  | Mech Room Electric Panel Replacements |  |  | 25000 |  |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  | 15000 | 25000 |  |  | 40000 |  | 40000
|  | Hall Carpet Replacement |  | 25000 |  |  |  | 25000 | 25000 | 50000 | Hall carpet is old and in need of replacement.
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 75000 | 75000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
JAMES PROPER
|  | Mech Room Electricial Panel Replacements |  |  |  | 25000 |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  | 25000 |  |  |  | 25000 |  | 25000
|  | Hall Carpet Replacement |  | 35000 |  |  |  | 35000 |  | 35000 | Hall carpet is old and in need of replacement.
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 95000 | 95000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Hall Director HVAC Unit | [5 empty] | 0 | 10000 | 10000 | Apartment HVAC for when building is vacant.
|  | Lobby Asbestos Abatement/Ceiling | [5 empty] | 0 | 50000 | 50000 | The replaces old ceiling after abatement.
|  | ADA ramp into building | [5 empty] | 0 | 35000 | 35000 | Construct wheelchair accessible ramp at the NW entrance.
|  | Replace Chiller #2 | [5 empty] | 0 | 125000 | 125000 | This replace 2nd Chiller, not yet critical.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
ROTARY HALL | [7 empty] | 0 |  | 0
|  | HVAC System Evaluation and Full Service |  | 15000 |  |  |  | 15000 |  | 15000 | HVAC needs full service and repairs.
|  | Replace Rotten wood on Dormers/Eaves |  | 50000 |  |  |  | 50000 |  | 50000 | A number of areas aroud the building have rotten wood/.
|  | Replace Chiller |  |  |  | 100000 |  | 100000 |  | 100000 | Chiller is one of the oldest on campus.
|  | Shower Updates | [5 empty] | 0 | 30000 | 30000 | Bathroom ad shower stalls needs repairs and updates.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
SEXTON HALL | [7 empty] | 0 |  | 0
|  | Mech Room Electric Panel Replacements |  | 25000 |  |  |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  | 25000 |  |  |  | 25000 |  | 25000
|  | Hall Carpet Replacement/Porch |  | 25000 |  |  |  | 25000 |  | 25000 | Hall carpet is old ad need of replacement.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 75000 | 75000 | Exterior building brick stained, mortar missing and needs sealed.
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Asbestos Abatement/Painting | [5 empty] | 0 | 250000 | 250000 | Final resident hall to have asbestos removed.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
GUEST/RENTAL PROPERTIES
|  | 2821 Woodlawn Updates for Rental | 0 | [7 empty] | Flooring, add kitchen, Painting, other maint. ON HOLD.
|  | 128 East Wilkinson and 953 Stephenson Updates | 5000 | [7 empty] | Painting, furniture, pictures, bedding. Other repairs.
|  | Bishop and President's Suite |  | 5000 | [6 empty] | Painting, furniture, pictures, bedding. Other repairs.
|  | Resident Hall Total: | 104000 | 273000 | 200000 | 125000 | 25000 | 717000 | 7685000 | 8402000